## Sheet1
Category | Task | Timeline
Initial Setup | Create Repository for integration agent | 3 Hours
Create client profile and test contract as well as integration agent contact
Setup RouteTemplate (Thresholds etc) and Actiontypes(service, delivery, collection, IBT, etc)
Development Phase | Create initial integration agent | 1 Workday
Create Model for Agent
Create Transformer for Agent
Create Listener for Agent
Setup external sources to aid the Agent (Logentries, mailgun, installer,Azure (Cosmos/Sql), etc)
Create Logging (SQL/Cosmos)
Set up Model for logging
Setup of Hosts files and xml configurations in Agent and link all external sources
Create tests for Agent using sample data
Testing Phase | Upload to correct profile | 1 Workday
Actions, decos and Entities are correct and matched to their types (adhoc, action types)
Logging to Sql/ Cosmos checked for integrity and reliability
Logentries logging data in the correct format
All data is matched with client sample information (invoices, DN’s, tripsheets)
Model been mapped and transformed correctly.
Writebacks | Create agent to write back data to FTP/SFTP,SOAP service | 1 Workday
Create view/api call to get required data
Map required data to DTOs
Write Data to endpoint
Live Testing Phase | Create Azure instance and publish/ deploy to Azure | 1 Workday
Test live deployment (Running test, sending files, logging, etc)
Update tripsheet (any other reporting)
Deploy new report for client profile
Load all personnel to client profile (driver information)
Load all vehicles to client profile (vehicle information)
Create test tripheet to test the reports
Test writeback (If applicable)
Refactor and Refinement | Make changes needed | 1 workday
Re-Run Testing Phase
Re-Run Live Testing Phase